## Çalışma Sayfası1
Task | Reporter | Assignee | Description | Estimation | Story Point | In Play | Playing | Review | In Review | Ready Of Test | Testing | Certify
ST-100 | Talat | Nazire | Student project create in start spring io. | 3h | 2
ST-101 | Talat | Nazire | Student list rest operation develop (getStudentList) Unit testleri ve MockMvc testleri yapılacak. | 2d | 3
ST-102 | Talat | Nazire | Student create rest operation develop. createStudentList(). You have to check what is there any same student in list. | 3d | 3
ST-103 | Talat | Nazire | Student find rest operation developments as a student id If you don't find any record with this student number. you have to throw custom error object.. getStudent(id) | 3d | 3
ST-104 | Talat | Nazire | Student update rest operation developments as a student If you don't find any record with this student number. you have to throw custom error object.. (put(id) | 2d | 2
ST-105 | Talat | Nazire | Student update rest operation developments as a student If you don't find any record with this student number. you have to throw custom error object.. PATCH(id) | 3d | 3
ST-106 | Talat | Nazire | Student delete of the rest operation development as a student id. | 2d | 2
ST-107 | Talat | Nazire | AOP integration For Logging | 3d | 3
ST-108 | Talat | Nazire | AOP integration For Performancing | 3d | 3
ST-109 | Talat | Nazire | Swagger integration | 3d | 3